## Summary
By epic
Epic ID | Epic | Stories | Sub-tasks | Story points | Hours | Done items | Due
E1 | Documentation & planning | 4 | 0 | 10 | 8.5 | 3 | 2026-10-07
E2 | Environment & infrastructure setup | 10 | 3 | 21 | 12.5 | 0 | 2026-10-08
E8 | STRETCH: Edge, nginx and subdomains | 4 | 0 | 7 | 3.5 | 0
E3 | MI common layer | 7 | 0 | 14 | 7 | 0 | 2026-10-09
E4 | Balance API: GET /accounts/{accountNumber}/balance | 4 | 0 | 8 | 4.5 | 0 | 2026-10-09
E5 | Customer API: GET /customers/{customerId} | 4 | 0 | 7 | 4 | 0 | 2026-10-09
E6 | Loan Eligibility API: POST /loans/eligibility | 6 | 0 | 14 | 7 | 0 | 2026-10-10
E7 | API Manager exposure | 7 | 0 | 17 | 9.5 | 0 | 2026-10-11
E10 | CI/CD pipeline (Jenkins) | 9 | 0 | 22 | 10.5 | 0 | 2026-10-12
E11 | Testing & QA | 5 | 0 | 8 | 3.5 | 0 | 2026-10-12
E9 | STRETCH: Observability, ELK | 5 | 0 | 11 | 5.5 | 0
E12 | Submission | 6 | 0 | 10 | 7 | 0 | 2026-10-12
E13 | Bonus (optional) | 2 | 0 | 13 | 7 | 0
Total |  | 73 | 3 | 162 | 90 | 3
Hours count stories only; sub-task hours are a breakdown of their parent story's estimate.
Daily load (story hours by due date)
Day | Date | Stories due | Hours | Capacity (h) | Over / (under)
Wed | 2026-10-07 | 6 | 11 | 11 | 0
Thu | 2026-10-08 | 11 | 13 | 13 | 0
Fri | 2026-10-09 | 12 | 12.5 | 13 | -0.5
Sat | 2026-10-10 | 9 | 12.5 | 13 | -0.5
Sun | 2026-10-11 | 12 | 13 | 13 | 0
Mon | 2026-10-12 | 12 | 12 | 13 | -1
Capacity (yellow): long days of 13 h Thu-Mon; Wed = 8 h docs already done + 3 h this evening. Edit to your real availability.
Formulas:
Due = IF(INDEX('Jira Import'!$L:$L,MATCH([Epic ID],'Jira Import'!$A:$A,0))="","",INDEX('Jira Import'!$L:$L,MATCH([Epic ID],'Jira Import'!$A:$A,0)))

## Jira Import
Issue ID | Issue Type | Summary | Description | Parent ID | Priority | Labels | Story Points | Original Estimate (h) | Original Estimate (s) | Start Date | Due Date | Component | Status | Epic (rollup)
E1 | Epic | Documentation & planning | BRD, Solution Design Document and Jira plan for the Jamii Savings integration platform. |  | Highest | docs |  |  |  | 2026-10-07 | 2026-10-07 | Docs | To Do | E1
S1.1 | Story | Business Requirements Document v1.1 | BRD covering scope, FR/NFR, error matrix, risks, acceptance and traceability. AC: final draft approved. | E1 | High | docs | 3 | 3 | 10800 | 2026-10-07 | 2026-10-07 | Docs | Done | E1
S1.2 | Story | Solution Design Document v1.1 with diagrams | Architecture, loan sequence, pipeline and edge topology diagrams; ADR log. AC: final draft approved. | E1 | High | docs | 5 | 4 | 14400 | 2026-10-07 | 2026-10-07 | Docs | Done | E1
S1.3 | Story | Jira project plan | This workbook: epics, stories, sub-tasks, estimates and dates. AC: imported into Jira. | E1 | High | docs | 1 | 1 | 3600 | 2026-10-07 | 2026-10-07 | Docs | Done | E1
S1.4 | Story | Create Jira project and import plan | Create project, import CSV, check hierarchy and dates. AC: board shows all epics and stories. | E1 | High | docs | 1 | 0.5 | 1800 | 2026-10-07 | 2026-10-07 | Docs | To Do | E1
E2 | Epic | Environment & infrastructure setup | Workstation, repository, WSO2 distributions, Docker images and docker-compose stack. |  | Highest | infrastructure |  |  |  | 2026-10-07 | 2026-10-08 | Infrastructure | To Do | E2
S2.1 | Story | Workstation prerequisites | Install and verify Docker (10-12 GB RAM allocated), JDK 21, Maven 3.9, apictl, curl, jq, Git and the MI VS Code extension. AC: versions recorded in README. | E2 | Highest | infrastructure | 2 | 1.5 | 5400 | 2026-10-07 | 2026-10-07 | Infrastructure | To Do | E2
T2.1.1 | Sub-task | Confirm supported JDK for chosen MI/APIM release | Check release notes; set base image JDK accordingly. | S2.1 | High | infrastructure |  | 0.5 | 1800 | 2026-10-07 | 2026-10-07 | Infrastructure | To Do | E2
S2.2 | Story | Git repository scaffold | Create repo per SDD section 10; .gitignore (dist zips, certs, .env), .env.example, README skeleton; push to GitHub. AC: clean clone shows full structure. | E2 | Highest | infrastructure | 1 | 1 | 3600 | 2026-10-07 | 2026-10-07 | Infrastructure | To Do | E2
S2.3 | Story | Download WSO2 APIM and MI distributions | Download latest matching 4.4.x zips into dist/; record SHA-256 in dist/checksums.txt. AC: checksums verified. | E2 | Highest | infrastructure | 1 | 0.5 | 1800 | 2026-10-08 | 2026-10-08 | Infrastructure | To Do | E2
S2.4 | Story | Build jamii/mi image | Multi-stage Dockerfile from eclipse-temurin + MI zip; non-root user; H2 driver in lib; log4j2 config; additional_contexts for dist. AC: container starts, management API answers on 9164. | E2 | Highest | infrastructure | 3 | 2 | 7200 | 2026-10-08 | 2026-10-08 | Infrastructure | To Do | E2
S2.5 | Story | Build jamii/apim image | Multi-stage Dockerfile from APIM zip; deployment.toml with public hostnames, proxy port 443, ELK analytics, admin creds from env; replace default keystores. AC: Publisher and Dev Portal log in on localhost:9443. | E2 | Highest | infrastructure | 5 | 3 | 10800 | 2026-10-08 | 2026-10-08 | Infrastructure | To Do | E2
T2.5.1 | Sub-task | Configure deployment.toml for localhost | Server hostname localhost; public hostnames and proxy port 443 are added with the nginx stretch (E8). | S2.5 | High | infrastructure |  | 1 | 3600 | 2026-10-08 | 2026-10-08 | Infrastructure | To Do | E2
T2.5.2 | Sub-task | Replace default keystores and admin credentials | Project self-signed keystore; admin password from env. | S2.5 | High | infrastructure |  | 1 | 3600 | 2026-10-08 | 2026-10-08 | Infrastructure | To Do | E2
S2.6 | Story | DB schema and seed scripts | db/schema.sql (accounts, CHECK on status) and db/seed.sql (one account per status plus a zero balance). AC: scripts run cleanly on H2. | E2 | Highest | infrastructure | 1 | 0.5 | 1800 | 2026-10-08 | 2026-10-08 | Infrastructure | To Do | E2
S2.7 | Story | Build jamii/h2 image | Temurin + H2 jar; RunScript schema and seed, then TCP server on 9092; healthcheck. AC: MI datasource connects. | E2 | Highest | infrastructure | 2 | 1 | 3600 | 2026-10-08 | 2026-10-08 | Infrastructure | To Do | E2
S2.8 | Story | Build jamii/wiremock image | Stubs mirroring the Beeceptor customer rules and DNE Divide, plus fault scenarios (delay, reset, SOAP fault). AC: stubs answer on 8089 and match beeceptor-rules.json. | E2 | High | infrastructure | 2 | 1 | 3600 | 2026-10-08 | 2026-10-08 | Infrastructure | To Do | E2
S2.9 | Story | docker-compose.yml with profiles | Services, jamii-net network, healthchecks, depends_on; profiles core, observability, ci. AC: compose --profile core up is healthy. | E2 | Highest | infrastructure | 3 | 1.5 | 5400 | 2026-10-08 | 2026-10-08 | Infrastructure | To Do | E2
S2.10 | Story | Local image registry and tagging | registry:2 service; images tagged with ${TAG} (build number). AC: push and pull work. | E2 | High | infrastructure | 1 | 0.5 | 1800 | 2026-10-08 | 2026-10-08 | Infrastructure | To Do | E2
E8 | Epic | STRETCH: Edge, nginx and subdomains | Stretch goal: start only after the pipeline is green. nginx as the single public entry with TLS and one subdomain per service under jamii.daqiqtech.co.ke. |  | Low | edge | [5 empty] | Edge | To Do | E8
S8.1 | Story | Build jamii/nginx image with server blocks | Server blocks for api., portal., apim., mi., kibana., jenkins. (dev: *.dev.jamii.daqiqtech.co.ke). AC: each host routes to its service. | E8 | Low | edge | 3 | 1.5 | 5400 |  |  | Edge | To Do | E8
S8.2 | Story | Wildcard TLS certificate and hosts entries | mkcert wildcard for *.dev.jamii.daqiqtech.co.ke; /etc/hosts entries to 127.0.0.1. AC: all six hosts load over HTTPS without warnings. | E8 | Low | edge | 1 | 0.5 | 1800 |  |  | Edge | To Do | E8
S8.3 | Story | Access controls on admin hosts | IP allowlist on apim., mi., kibana., jenkins.; client_max_body_size 50m on apim.; proxy_ssl_verify off for internal HTTPS. AC: non-allowlisted IP gets 403. | E8 | Low | edge | 2 | 1 | 3600 |  |  | Edge | To Do | E8
S8.4 | Story | Verify edge security | Confirm MI 8290, Elasticsearch, H2 and registry are unreachable from outside the Docker network. AC: evidence in README. | E8 | Low | edge | 1 | 0.5 | 1800 |  |  | Edge | To Do | E8
E3 | Epic | MI common layer | Shared sequences, templates and class mediator used by all three APIs. |  | Highest | mi-common |  |  |  | 2026-10-08 | 2026-10-09 | MI Common | To Do | E3
S3.1 | Story | MI multi-module Maven project | Modules: common, balance-api, customer-api, loan-api, composite. AC: mvn clean install builds a CAR. | E3 | Highest | mi-common | 2 | 1 | 3600 | 2026-10-08 | 2026-10-08 | MI Common | To Do | E3
S3.2 | Story | Common_InSeq: correlation ID | Read or generate X-Correlation-ID (UUID v4); store as property; record start time. AC: ID returned on every response. | E3 | Highest | mi-common | 1 | 0.5 | 1800 | 2026-10-08 | 2026-10-08 | MI Common | To Do | E3
S3.3 | Story | MaskingMediator class mediator | Mask account numbers (last 4) and PII fields; drop financial amounts. AC: JUnit tests pass. | E3 | Highest | mi-common | 3 | 1.5 | 5400 | 2026-10-08 | 2026-10-08 | MI Common | To Do | E3
S3.4 | Story | Common_MaskedLog template | Logs REQUEST_IN, BACKEND_CALL, RESPONSE_OUT as key=value with masked fields. AC: three lines per request, no raw PII. | E3 | Highest | mi-common | 2 | 1 | 3600 | 2026-10-09 | 2026-10-09 | MI Common | To Do | E3
S3.5 | Story | Common_ErrorResponse template | Builds standard error JSON (code, message, httpStatus, details, requestId, timestamp). AC: validates against error schema. | E3 | Highest | mi-common | 2 | 1 | 3600 | 2026-10-09 | 2026-10-09 | MI Common | To Do | E3
S3.6 | Story | Common_FaultSeq | Classify timeout (504), connection (503), SQL (503 DB_UNAVAILABLE), malformed JSON (400), other (500). AC: no stack trace ever returned. | E3 | Highest | mi-common | 3 | 1.5 | 5400 | 2026-10-09 | 2026-10-09 | MI Common | To Do | E3
S3.7 | Story | Common_HeaderHygiene | Strip X-Internal-*, Server, X-Powered-By, Set-Cookie inbound and outbound. AC: headers absent in responses. | E3 | High | mi-common | 1 | 0.5 | 1800 | 2026-10-09 | 2026-10-09 | MI Common | To Do | E3
E4 | Epic | Balance API: GET /accounts/{accountNumber}/balance | DB-backed API using MI Data Services over H2. |  | Highest | balance-api |  |  |  | 2026-10-09 | 2026-10-09 | Balance API | To Do | E4
S4.1 | Story | Datasource JamiiAccountsDS | JDBC pool to jdbc:h2:tcp://h2:9092/jamii; credentials from env. AC: pool connects at startup. | E4 | Highest | balance-api | 1 | 0.5 | 1800 | 2026-10-09 | 2026-10-09 | Balance API | To Do | E4
S4.2 | Story | AccountsDataService parameterised query | getAccountByNumber with a bound parameter. AC: no string-built SQL. | E4 | Highest | balance-api | 2 | 1 | 3600 | 2026-10-09 | 2026-10-09 | Balance API | To Do | E4
S4.3 | Story | BalanceAPI resource and envelope | Regex validation (400), envelope via PayloadFactory, 404 ACCOUNT_NOT_FOUND, 503 DB_UNAVAILABLE. AC: matches BRD 8.2 envelope. | E4 | Highest | balance-api | 3 | 2 | 7200 | 2026-10-09 | 2026-10-09 | Balance API | To Do | E4
S4.4 | Story | Balance API unit tests | MI unit test suite for 200, 400, 404 against the H2 container. AC: tests run in mvn build. | E4 | High | balance-api | 2 | 1 | 3600 | 2026-10-09 | 2026-10-09 | Balance API | To Do | E4
E5 | Epic | Customer API: GET /customers/{customerId} | Managed proxy in front of a Beeceptor mock endpoint with gateway value; WireMock mirror for CI. |  | Highest | customer-api |  |  |  | 2026-10-09 | 2026-10-09 | Customer API | To Do | E5
S5.1 | Story | CustomerBackendEP | HTTP endpoint with 5 s timeout and configurable base URL (Beeceptor for demo, WireMock for CI). AC: switch backend by env var only. | E5 | Highest | customer-api | 1 | 0.5 | 1800 | 2026-10-09 | 2026-10-09 | Customer API | To Do | E5
S5.0 | Story | Beeceptor endpoint and rules | Create the Beeceptor endpoint; rules for /customers/1001-1005 (200, bank-shaped records with national ID, +254 phone, KYC status), 9999 (404), 5000 (500), 5004 (7 s delay); export to mocks/beeceptor-rules.json; check free-tier quota. AC: all four rules answer; export committed. | E5 | Highest | customer-api | 1 | 0.5 | 1800 | 2026-10-09 | 2026-10-09 | Customer API | To Do | E5
S5.2 | Story | CustomerAPI resource | Validation (400), header hygiene, correlation ID, 404 CUSTOMER_NOT_FOUND, 504 timeout, 503 unavailable via fault sequence. AC: all paths return the standard error body. | E5 | Highest | customer-api | 3 | 2 | 7200 | 2026-10-09 | 2026-10-09 | Customer API | To Do | E5
S5.3 | Story | Customer API tests | MI unit test suite with a mock service for CustomerBackendEP (200, 404, 5xx); WireMock delay for 504. AC: 404, 503 and 504 proven. | E5 | High | customer-api | 2 | 1 | 3600 | 2026-10-09 | 2026-10-09 | Customer API | To Do | E5
E6 | Epic | Loan Eligibility API: POST /loans/eligibility | REST/JSON to SOAP (DNE Calculator Divide) with fault mapping. |  | Highest | loan-api |  |  |  | 2026-10-10 | 2026-10-10 | Loan API | To Do | E6
S6.1 | Story | Request JSON schema and validation | loan-request.schema.json via Validate mediator; 400 with field details. AC: missing or wrong-typed fields return 400. | E6 | Highest | loan-api | 2 | 1 | 3600 | 2026-10-10 | 2026-10-10 | Loan API | To Do | E6
S6.2 | Story | JSON to SOAP Divide mapping | intA = (existingMonthlyDebt + requestedMonthlyInstalment) x 100; intB = monthlyIncome. AC: correct SOAP envelope logged (masked). | E6 | Highest | loan-api | 3 | 1.5 | 5400 | 2026-10-10 | 2026-10-10 | Loan API | To Do | E6
S6.3 | Story | SOAP to JSON decision | DivideResult = DTI %; ELIGIBLE when 40 or less; response per SDD 4.3. AC: clean JSON, no XML. | E6 | Highest | loan-api | 2 | 1 | 3600 | 2026-10-10 | 2026-10-10 | Loan API | To Do | E6
S6.4 | Story | SOAP fault and transport error mapping | Divide-by-zero fault -> 422 ELIGIBILITY_REJECTED; other faults -> 502; 10 s timeout -> 504; unreachable -> 503. AC: no SOAP XML ever reaches the client. | E6 | Highest | loan-api | 3 | 1.5 | 5400 | 2026-10-10 | 2026-10-10 | Loan API | To Do | E6
S6.5 | Story | Loan API tests | MI unit test suite with a mock service returning DivideResult and SOAP faults; WireMock delay for 504. AC: 200, 400, 422, 502, 504 proven. | E6 | High | loan-api | 2 | 1 | 3600 | 2026-10-10 | 2026-10-10 | Loan API | To Do | E6
S6.6 | Story | Bake CARs into jamii/mi image | Build CARs, copy into image, redeploy; verify all three APIs live on MI. AC: MI management API lists 3 APIs. | E6 | Highest | loan-api | 2 | 1 | 3600 | 2026-10-10 | 2026-10-10 | Loan API | To Do | E6
E7 | Epic | API Manager exposure | OpenAPI, security, tiers, mediation policy, API Product and Developer Portal for all three APIs. |  | Highest | api-manager |  |  |  | 2026-10-10 | 2026-10-11 | API Manager | To Do | E7
S7.1 | Story | OpenAPI 3.0 definitions x3 | Paths, parameter patterns, request/response schemas, all error responses via shared ErrorResponse. AC: spectral lint clean. | E7 | Highest | api-manager | 3 | 2 | 7200 | 2026-10-10 | 2026-10-10 | API Manager | To Do | E7
S7.2 | Story | Custom tier LoanCheck-10PerMin | Subscription tier for the Loan API. AC: tier visible in Publisher. | E7 | Highest | api-manager | 1 | 0.5 | 1800 | 2026-10-10 | 2026-10-10 | API Manager | To Do | E7
S7.3 | Story | apictl projects x3 | api.yaml, OAS, endpoints via api_params.yaml (dev/prod); OAuth2 (Balance, Loan), API Key (Customer); Gold / LoanCheck tiers. AC: apictl import succeeds for all three. | E7 | Highest | api-manager | 5 | 3 | 10800 | 2026-10-10 | 2026-10-10 | API Manager | To Do | E7
S7.4 | Story | Custom policy jamii-gateway-context | Operation policy (.j2 + .yaml) on Balance API: inject X-Correlation-ID and X-Channel, strip Authorization. AC: headers visible in MI logs. | E7 | Highest | api-manager | 3 | 1.5 | 5400 | 2026-10-11 | 2026-10-11 | API Manager | To Do | E7
S7.5 | Story | API Product Jamii Retail Banking | Bundle all three APIs; OAuth2, Gold tier. AC: one subscription grants access to all three. | E7 | Highest | api-manager | 2 | 1 | 3600 | 2026-10-11 | 2026-10-11 | API Manager | To Do | E7
S7.6 | Story | apictl environments and publish | Add dev env (localhost) and prod env (placeholder hostnames); import, publish, generate keys, call the gateway on localhost:8243. AC: 401 without token, 200 with token. | E7 | Highest | api-manager | 2 | 1 | 3600 | 2026-10-11 | 2026-10-11 | API Manager | To Do | E7
S7.7 | Story | Developer Portal onboarding guide | README section with steps and screenshots for discover, subscribe, generate keys, call. AC: a new app can follow it unaided. | E7 | High | api-manager | 1 | 0.5 | 1800 | 2026-10-11 | 2026-10-11 | API Manager | To Do | E7
E10 | Epic | CI/CD pipeline (Jenkins) | One declarative Jenkinsfile for all three APIs with dev and prod stages and rollback. |  | Highest | ci/cd |  |  |  | 2026-10-11 | 2026-10-12 | CI/CD | To Do | E10
S10.1 | Story | Build jamii/jenkins image | JDK 21, Maven, apictl, curl, jq, Docker CLI, plugins.txt; MI unpacked from the dist volume for unit tests. AC: Jenkins reachable on localhost:8080. | E10 | Highest | ci/cd | 2 | 1 | 3600 | 2026-10-11 | 2026-10-11 | CI/CD | To Do | E10
S10.2 | Story | Jenkins credentials and job | APIM admin, DB, registry credentials; pipeline job from Git; dist volume mounted. AC: job checks out repo. | E10 | Highest | ci/cd | 1 | 0.5 | 1800 | 2026-10-11 | 2026-10-11 | CI/CD | To Do | E10
S10.3 | Story | Jenkinsfile: validate and build stages | Checkout, Validate (xmllint, spectral, apictl), Build MI (mvn + unit tests), build and push all images; loop over APIS list. AC: green build to registry. | E10 | Highest | ci/cd | 5 | 2.5 | 9000 | 2026-10-11 | 2026-10-11 | CI/CD | To Do | E10
S10.4 | Story | Jenkinsfile: package APIM stage | Package three apictl projects and the product as artifacts. AC: archives archived per build. | E10 | Highest | ci/cd | 2 | 1 | 3600 | 2026-10-11 | 2026-10-11 | CI/CD | To Do | E10
S10.5 | Story | Jenkinsfile: deploy dev stage | Save rollback point (current tag + exported APIs), swap MI image, wait for health, apictl import loop with set -e. AC: all three updated or none. | E10 | Highest | ci/cd | 5 | 2 | 7200 | 2026-10-11 | 2026-10-11 | CI/CD | To Do | E10
S10.6 | Story | Jenkinsfile: test dev stage | gateway-check.sh (401, 200, 429, product subscription) and masked-log grep. AC: any failure fails the build. | E10 | Highest | ci/cd | 2 | 1 | 3600 | 2026-10-11 | 2026-10-11 | CI/CD | To Do | E10
S10.7 | Story | Rollback on failure | post { failure } runs rollback.sh: previous MI image and re-import previous API archives. AC: forced failure leaves dev unchanged. | E10 | Highest | ci/cd | 3 | 1.5 | 5400 | 2026-10-12 | 2026-10-12 | CI/CD | To Do | E10
S10.8 | Story | Prod stage with approval | input approval; same artifacts; apictl env prod (dry run). AC: stage pauses for approval. | E10 | High | ci/cd | 1 | 0.5 | 1800 | 2026-10-12 | 2026-10-12 | CI/CD | To Do | E10
S10.9 | Story | Prove no partial deploy | Break one API import deliberately; capture failed run and rollback evidence. AC: screenshots in README. | E10 | High | ci/cd | 1 | 0.5 | 1800 | 2026-10-12 | 2026-10-12 | CI/CD | To Do | E10
E11 | Epic | Testing & QA | Functional, contract, throttling, fault and masking tests. |  | Highest | testing |  |  |  | 2026-10-11 | 2026-10-12 | Testing | To Do | E11
S11.1 | Story | MI unit test runtime in CI | Configure the MI unit test plugin to run against MI unpacked from dist/ on the Jenkins agent; H2 container available for Balance tests. AC: mvn clean install runs all MI test suites in Jenkins. | E11 | Highest | testing | 2 | 0.5 | 1800 | 2026-10-11 | 2026-10-11 | Testing | To Do | E11
S11.2 | Story | Error contract assertions | JSON-path assertions ($.error.code, $.error.httpStatus, $.requestId, $.timestamp) in every MI error test. AC: all three APIs pass. | E11 | Highest | testing | 1 | 0.5 | 1800 | 2026-10-11 | 2026-10-11 | Testing | To Do | E11
S11.3 | Story | gateway-check.sh | curl script with exit codes: 401 without token, 200 with token, 429 past LoanCheck-10PerMin, product subscription grants all three APIs. AC: script fails on any mismatch. | E11 | High | testing | 2 | 1 | 3600 | 2026-10-12 | 2026-10-12 | Testing | To Do | E11
S11.4 | Story | Fault drills | Stop H2 -> 503; WireMock delay -> 504; SOAP fault -> 422. AC: all observed and recorded. | E11 | Highest | testing | 2 | 1 | 3600 | 2026-10-12 | 2026-10-12 | Testing | To Do | E11
S11.5 | Story | Log masking verification | grep MI logs for full account numbers or PII (Elasticsearch check added if ELK stretch is done). AC: zero hits. | E11 | Highest | testing | 1 | 0.5 | 1800 | 2026-10-12 | 2026-10-12 | Testing | To Do | E11
E9 | Epic | STRETCH: Observability, ELK | Stretch goal: start only after the pipeline is green. Filebeat, Logstash, Elasticsearch and Kibana with dashboards and correlation-ID tracing. |  | Low | observability | [5 empty] | Observability | To Do | E9
S9.1 | Story | Elasticsearch and Kibana services | Security on (password from .env), heap caps, healthchecks. AC: Kibana loads at kibana.dev host. | E9 | Low | observability | 2 | 1 | 3600 |  |  | Observability | To Do | E9
S9.2 | Story | Build jamii/filebeat image | Inputs for MI logs and APIM apim_metrics.log on shared volumes. AC: events reach Logstash. | E9 | Low | observability | 2 | 1 | 3600 |  |  | Observability | To Do | E9
S9.3 | Story | Build jamii/logstash image and pipeline | kv for MI, json for APIM, date, re-mask regex, routing to jamii-mi-* and jamii-apim-analytics-*. AC: fields parsed. | E9 | Low | observability | 3 | 1.5 | 5400 |  |  | Observability | To Do | E9
S9.4 | Story | Kibana dashboard and kibana-setup image | Data views plus 5 panels (requests, error rate, p95 latency, 429s, trace search); ndjson imported at start; 7-day ILM. AC: dashboard populated after test run. | E9 | Low | observability | 3 | 1.5 | 5400 |  |  | Observability | To Do | E9
S9.5 | Story | End-to-end trace check | Trace one request by correlation ID across APIM and MI. AC: screenshot for README and video. | E9 | Low | observability | 1 | 0.5 | 1800 |  |  | Observability | To Do | E9
E12 | Epic | Submission | README, docs export, presentation, demo video and repository submission. |  | Highest | submission |  |  |  | 2026-10-12 | 2026-10-12 | Submission | To Do | E12
S12.1 | Story | README.md | Architecture decisions and trade-offs, what with more time, assumptions, how to run locally (half to one page). AC: clean clone runs by following it. | E12 | Highest | submission | 2 | 1.5 | 5400 | 2026-10-12 | 2026-10-12 | Submission | To Do | E12
S12.2 | Story | Export BRD and SDD to docs/ | PDF exports committed under docs/. AC: links in README. | E12 | High | submission | 1 | 0.5 | 1800 | 2026-10-12 | 2026-10-12 | Submission | To Do | E12
S12.3 | Story | Presentation deck | Problem, architecture, three APIs, APIM, pipeline, trade-offs, next steps (observability and edge if stretch done). AC: rehearsed in under 10 minutes. | E12 | Highest | submission | 3 | 2 | 7200 | 2026-10-12 | 2026-10-12 | Submission | To Do | E12
S12.4 | Story | Demo script and dry run | Script one live call per API plus failure paths (Kibana trace if ELK stretch done). AC: fits 5 minutes. | E12 | Highest | submission | 1 | 1 | 3600 | 2026-10-12 | 2026-10-12 | Submission | To Do | E12
S12.5 | Story | Record 5-minute screen recording | Live call to each of the three APIs through the gateway. AC: video linked in README. | E12 | Highest | submission | 2 | 1 | 3600 | 2026-10-12 | 2026-10-12 | Submission | To Do | E12
S12.6 | Story | Final repo check and submit | Fresh clone, compose up, MI unit tests and gateway-check.sh green, secrets scan; submit Git link. AC: submitted by 12 Oct. | E12 | Highest | submission | 1 | 1 | 3600 | 2026-10-12 | 2026-10-12 | Submission | To Do | E12
E13 | Epic | Bonus (optional) | Only after every core acceptance criterion passes. |  | Low | bonus | [5 empty] | Bonus | To Do | E13
S13.1 | Story | Bonus A: customer dashboard aggregation | Scatter-gather Customer + Balance in parallel; partial data with failed section flagged; 503 if both fail. | E13 | Low | bonus | 5 | 3 | 10800 |  |  | Bonus | To Do | E13
S13.2 | Story | Bonus B: RabbitMQ loan events with DLQ | Inbound consumer, transform, call Loan API, publish decision; DLQ for malformed messages; 3 retries with backoff. | E13 | Low | bonus | 8 | 4 | 14400 |  |  | Bonus | To Do | E13

## How to import
How to import into Jira
1. Jira imports CSV, not .xlsx. Use the companion file jamii-jira-import.csv (same rows, computed values).
2. Jira: Settings (cog) > System > External System Import > CSV (company-managed), or Project > Import work items (team-managed).
3. Date format setting: yyyy-MM-dd. File encoding: UTF-8.
4. Field mapping: Issue ID > Issue Id; Parent ID > Parent Id; Issue Type, Summary, Description, Priority, Labels, Component, Status, Due Date, Start Date as named; Story Points > Story point estimate; Original Estimate (s) > Original Estimate.
5. Do not map 'Original Estimate (h)' or 'Epic (rollup)'; they exist for this workbook's Summary sheet.
6. Status 'Done' only imports if your workflow has a Done status; otherwise map it to the nearest status.
7. If Components do not exist in the project yet, let the importer create them or create them first.
Editing
Edit rows on 'Jira Import'. The Summary sheet recalculates. Yellow cells on Summary are the only manual inputs.